## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | Web Development
INTERN NAME: | Naman Rajesh Shah
PROJECT NAME: | Create website to find colleges in India
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 26/04/2026
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
What went well+A45A19:A44A19:A45
1. Successfully designed clean UI for searching colleges
2. Implemented search
3. learned how to connect frontend with backend
4. Complete project within deadline
Challenges faced
1. Difficulty managing large dataset
2. Search result not getting accurate
3. Confusion in database structure
How I solved them
1. Optimise database queries for better search
2. Reorganized database schema
Tools & Tech used
1. HTML, CSS, Javascript, Python
2. SQL
3. Some AI tools like (Chatgpt/ gemini cli)
Key learnings
1. Importance of planning databse
2. UI/UX plays a major role
3. Testing is necessary at every stage
Conclusion
This project imroved my practical web development skills and understanding of real world problem solving

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME |  |  |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT ID
PROJECT MANAGER
PROJECT SPONSOR
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 20/04/2026 | Search results were inaccurate | Technical | Incorrect result during testing | Improve search logic and filtering | Optimize query | Developer | SOLVED | Accuracy improved after fix
| 22/04/2026 | Website not responsive on mobile | UI/UX | Layout breaking on small screen | Use responsive design from start | Added media queries | Frontend Developer | SOLVED | Works properly
| 24/04/2026 | Slow website performance | Technical | Long time loading | optimize queries | improved queries | Developer | SOLVED | Faster loading