## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | Create a website to find colleges in India (Web development)
PROJECT SPONSOR | Tushar Topale
PROJECT MANAGER | Harshada Topale
EXPECTED START DATE | 2026-04-08
EXPECTED COMPLETION DATE | 2026-04-26
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | The objective of this project is to develop a web based application that allows users to search for colleges in India based on name, course, and other criteria. The system aims to provide accurate college information, including contact details on google and available courses, in a user-friendly and efficient manner.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | The need for a centralized platform to search colleges arises due to scattered and unorganized information available online. This project provides a simple solution where users can easily find colleges and relevant details in one place. Benefits: Saves time for students searching for colleges Provides organized and accessible data Improves decision making for students
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | Successfully develop and deploy the website within the given timeline Ensure search results accuracy above 90% Achieve fast loading time (within 1–2 seconds) Ensure responsive design across mobile and desktop devices Minimize critical bugs
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | Fully functional College Finder Website Search and filter functionality for colleges College details page with relevant information Responsive user interface (mobile + desktop) Database containing college data
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | Search colleges by name Filter colleges based on course/degree (e.g., B.Tech, M. Tech) Display college details (name, location, contact info, courses) Responsive design for mobile and desktop Basic database integration to store and retrieve college data Simple and user-friendly UI Navigation between pages (home, finder, compare)
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | User login/signup system Personalized recommendations Online admission/application system Payment gateway integration Advanced filters (ranking, reviews) Admin dashboard for managing data Chat support or AI-based suggestions
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Total Members: 1 (Individual Project) Roles: Developer : Responsible for frontend, backend, database, and testing
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | Hardware: Laptop/Desktop Internet connection Software: Code Editor (VS Code) Web Browser (Chrome/Edge) Database (MySQL / SQL) Other Resources: College dataset (for database/Kaggle)
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | N/A
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Naman Shah (Developer)
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | Only developer
END CUSTOMER (Mention the client name.) | Studnets
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | Inaccurate or incomplete college data Search functionality may not return correct results Website performance issues with large data Bugs in UI or database integration Browser compatibility issues
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | Users have internet access and modern browsers Users will enter proper search keywords System will not require frequent real time updates
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | Limited development time (academic deadline) Limited resources (single developer ) Limited budget (mostly free tools) Limited dataset availability with limited resources in it Basic technology stack (HTML, CSS, JS, SQL,Python only)
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document") | Completion Date: 04-10-2026 Requirement gathering is marked.
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs") | Completion Date: 04-14-2026 Planning phase is considered.
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 04-18-2026 Design stage is considered complete.
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files") | Completion Date: 04-22-2026 Development stage is considered complete after implementation of frontend, backend, and database.
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports") | Completion Date: 04-24-2026 Testing stage is considered complete.
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ") | Completion Date: 04-24-2026 Deployment stage is considered complete after hosting the website on server/local environment.
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide") | Completion Date: 04-26-2026 Project closure is considered complete after submission of lessons learned log, final report, and installation guide.